## Master Action Plan
KOMPLAI ¦ PROJECT HAIL MARY — MASTER ACTION PLAN
Larry Self-Serve Launch ¦ Feb 17 – Sep 30, 2026 ¦ Owners: Rishi (GTM/Strategy), Anirudh (Product/Engineering)
ID | Phase | Category | Task | Sub-tasks / Details | Owner | Priority | Dependency | Start Date | End Date | Days | Status | Success Metric | Notes / Risk
WEEK 1: Feb 17-21 — Foundation Sprint
1 | Phase 0: Pre-Launch | Product | Self-serve onboarding flow: end-to-end audit | Map every screen from signup → ERP connect → first Larry insight. Document every click, every load time, every error state. Record screen captures of the full flow for all 4 ERPs (Zoho, QBO, ERPNext, Xero). | Anirudh | P0 - Critical | None | 2026-02-17 | 2026-02-19 | 3 | Not Started | Full flow documented with screenshots for all 4 ERPs | This is THE most important task. Nothing else matters if onboarding is broken.
2 | Phase 0: Pre-Launch | Product | Build pre-populated first queries for Larry | After ERP sync, Larry should suggest 3-5 data-specific queries (not generic). If user has overdue receivables → suggest aging analysis. If burn spiked → suggest burn analysis. Requires conditional logic based on synced data. | Anirudh | P0 - Critical | Onboarding audit complete | 2026-02-19 | 2026-02-28 | 10 | Not Started | Larry suggests personalized queries within 60 seconds of ERP sync | The difference between 'ask Larry anything' and 'Larry already found something' is the difference between activation and abandonment.
3 | Phase 0: Pre-Launch | Product | Build 'wow moment' automated email | Triggered 15-30 min after ERP sync completes. Email must contain 2-3 REAL insights from the user's actual data. E.g., 'Larry found $47K in receivables over 90 days across 10 invoices.' Requires email template + dynamic data pipeline. | Anirudh | P0 - Critical | Pre-populated queries built | 2026-02-24 | 2026-03-05 | 10 | Not Started | Email sends within 30 min of ERP sync with real data points | This email is the single most important piece of marketing you will produce.
4 | Phase 0: Pre-Launch | Product | Build guided product walkthrough (3-step tour) | Interactive overlay (not video): Step 1 → first query, Step 2 → first chart, Step 3 → attempt download (gates on Scaling tier). Must complete in under 2 minutes. Use product tour library (e.g., Shepherd.js or similar). | Anirudh | P1 - High | Onboarding audit complete | 2026-02-20 | 2026-03-03 | 12 | Not Started | Tour completion rate >60% of new users | Keep it short. 3 steps max. Users who complete onboarding tours convert 2-3x better.
5 | Phase 0: Pre-Launch | Product | Build error handling for ERP sync failures | Specific error states for: OAuth failure, timeout, partial data sync, unsupported ERP version. Each error must show: what went wrong, how to fix it, and a path to retry or get help. No generic error pages. | Anirudh | P0 - Critical | Onboarding audit complete | 2026-02-19 | 2026-02-26 | 8 | Not Started | Zero generic 'something went wrong' screens | A failed ERP connection with no recovery path = permanent user loss.
6 | Phase 0: Pre-Launch | Product | Instrument full funnel tracking (10 events) | Track: website visit, signup initiated, signup completed, ERP connection started, ERP connection completed, first Larry query, first chart generated, upgrade prompt shown, upgrade initiated, upgrade completed. Use Mixpanel/Amplitude + Segment. | Anirudh | P0 - Critical | None | 2026-02-17 | 2026-02-24 | 8 | Not Started | All 10 events firing correctly in analytics dashboard | You cannot optimize what you do not measure. Non-negotiable before launch.
7 | Phase 0: Pre-Launch | Product | Instrument engagement metrics | Track: questions per session, questions per day, return rate (Day 1, 3, 7), feature usage (Analyze vs Explain vs Search vs Identify), Close Tracker views. | Anirudh | P1 - High | Funnel tracking complete | 2026-02-24 | 2026-02-28 | 5 | Not Started | Engagement dashboard live with daily refresh | Engagement data drives every decision in May.
8 | Phase 0: Pre-Launch | Product | Build sales handoff trigger notifications | 5 triggers auto-notify sales (Rishi initially): (1) User hits 10-question daily limit, (2) User asks about multi-entity, (3) Close Tracker shows bottlenecks, (4) Company matches ICP (Series B+, 10+ team), (5) User asks about Book Close. Slack/email notification with user context. | Anirudh | P1 - High | Engagement metrics built | 2026-02-28 | 2026-03-07 | 8 | Not Started | All 5 triggers tested and firing correctly | Leads without a sales process are wasted. This bridges product to revenue.
9 | Phase 0: Pre-Launch | Product | Build in-product upgrade prompts + flow | When users hit free tier limits (10 questions/day, no downloads, 7-day history), show contextual upgrade modal: what they unlock, price, 1-click upgrade. No redirect to external pricing page. Upgrade must happen in context. | Anirudh | P1 - High | Funnel tracking complete | 2026-02-26 | 2026-03-07 | 10 | Not Started | Upgrade flow <3 clicks from limit hit to payment confirmed | Ambiguity kills self-serve conversion. Make it frictionless.
10 | Phase 0: Pre-Launch | Product | Implement geo-based pricing display | Auto-detect user geography. Show $199/mo for US, $99/mo for India. Never show both prices on same screen. Annual toggle: $199/mo or $1,990/year (2 months free). | Anirudh | P2 - Medium | Upgrade flow built | 2026-03-07 | 2026-03-12 | 6 | Not Started | Correct pricing shown based on geo for 10 test locations | Showing both prices creates confusion and arbitrage.
11 | Phase 0: Pre-Launch | Product | Load test all 4 ERP integrations | Simulate 100+ concurrent ERP connections across Zoho, QBO, ERPNext, Xero. Test: connection time, data sync time, data completeness, error rates. Fix anything that takes >30 min. | Anirudh | P0 - Critical | None | 2026-03-17 | 2026-03-24 | 8 | Not Started | All 4 ERPs sync <30 min with <5% error rate at 100 concurrent users | If this fails at scale on April 1, nothing else matters.
12 | Phase 0: Pre-Launch | Product | Quality-test Larry against 50 real datasets | Run Larry against 50 different ERP data exports. Check: accuracy of insights, appropriateness of suggestions, handling of edge cases (empty data, partial data, unusual COA structures). Document failures. | Anirudh | P0 - Critical | Pre-populated queries built | 2026-03-10 | 2026-03-24 | 15 | Not Started | Larry produces accurate answers for >90% of test queries | Larry giving wrong/misleading answers = trust destroyed permanently.
13 | Phase 0: Pre-Launch | Product | Build Close Tracker basic progress view (Starter tier) | Minimal viable Close Tracker: show % of transactions reconciled, # journal entries posted, visual progress bar. No timeline predictions (Scaling+ only). Position as 'Larry observes your close.' | Anirudh | P1 - High | None | 2026-02-24 | 2026-03-14 | 19 | Not Started | Close Tracker shows accurate progress for test accounts | This is the wedge into paid. It must work at launch.
14 | Phase 0: Pre-Launch | Product | Final QA: 10 test users complete full flow | Recruit 10 people (mix of internal + friendly external). Each must: sign up, connect ERP, ask Larry questions, view Close Tracker, attempt download (hit paywall), complete upgrade. Document every friction point. | Anirudh | P0 - Critical | All product tasks above | 2026-03-24 | 2026-03-28 | 5 | Not Started | 10/10 users complete flow with zero critical bugs | Ship-blocking. If this fails, delay launch.
WEEK 1-2: Feb 17-28 — GTM Foundation
15 | Phase 0: Pre-Launch | Marketing | Rewrite top 20 SEO article titles + meta descriptions | Sort existing blog articles by impressions (Google Search Console). Take top 20. Rewrite titles using benefit+timeframe formula: 'Cut Month-End Close from 10 Days to 3: [Topic] Guide [2026].' Update meta descriptions with result + proof + emotion formula. | Rishi | P1 - High | None | 2026-02-17 | 2026-02-21 | 5 | Not Started | 20 articles updated; CTR improvement tracked weekly | Your articles rank but don't get clicks. This is the highest-ROI marketing activity right now.
16 | Phase 0: Pre-Launch | Marketing | LinkedIn posts: Weeks 3-4 of content plan | Continue 3x/week cadence. Posts 7-12 per the content plan: Maker-Checker Framework, One-Person Finance Team Org Chart, Data Entry Waste Calculator, Stale Data Warning System, Institutional Memory, 30-Min Integration Checklist. | Rishi | P1 - High | None | 2026-02-17 | 2026-02-28 | 12 | Not Started | 6 posts published, engagement rate tracked | Protect this time ruthlessly. LinkedIn organic is your #1 channel.
17 | Phase 0: Pre-Launch | Sales | Draft sales handoff email templates (5 triggers) | Write personalized outreach templates for each of the 5 sales triggers. Each must reference the user's actual Larry usage. E.g., for question-limit trigger: 'I noticed you've been asking Larry about [X]. Companies like yours typically save [Y] hours with our full platform.' | Rishi | P1 - High | None | 2026-02-17 | 2026-02-21 | 5 | Not Started | 5 templates drafted and ready for trigger integration | When a trigger fires, there must be zero delay in knowing what to say.
18 | Phase 0: Pre-Launch | Marketing | Reach out to 10 finance influencers/newsletter operators | Identify 10 people: finance LinkedIn creators, accounting newsletter authors, CFO community leaders. Send personal DM offering early Larry access on their own books. Ask for honest reaction, not a testimonial. Target: 5+ accept. | Rishi | P1 - High | None | 2026-02-17 | 2026-02-24 | 8 | Not Started | 5+ influencers confirmed for early access | Authentic reactions from real finance professionals > any ad spend.
19 | Phase 0: Pre-Launch | Marketing | Set up Google AdWords campaigns (do NOT activate yet) | Create campaigns: (1) Branded: 'Komplai,' 'Larry AI finance.' (2) Long-tail: 'MIS automation,' 'AI finance assistant,' 'why does month end close take so long.' (3) Competitor: 'Numeric alternatives,' 'FloQast alternative for startups.' Create ad copy + landing pages for each. | Rishi | P1 - High | None | 2026-02-24 | 2026-03-07 | 12 | Not Started | 3 campaign groups ready with ads + landing pages | Do NOT bid on expensive category terms ($20-40/click). Only long-tail and branded.
20 | Phase 0: Pre-Launch | Marketing | Build comparison landing pages (3 pages) | Create: Komplai vs Numeric, Komplai vs FloQast, Komplai vs BlackLine. Use competitive intel from your docs. Honest comparison: where you win, where they win. CTA: 'Try Larry free and see for yourself.' | Rishi | P2 - Medium | Google AdWords setup | 2026-03-03 | 2026-03-10 | 8 | Not Started | 3 landing pages live with tracked conversion events | These catch bottom-funnel traffic from competitor search queries.
21 | Phase 0: Pre-Launch | Marketing | Install LinkedIn retargeting pixel on website | Install LinkedIn Insight Tag. Define audience: CFO, Controller, Finance Director, VP Finance job titles. Build retargeting audience from website visitors. Do NOT activate ads yet. | Rishi | P2 - Medium | None | 2026-02-17 | 2026-02-19 | 3 | Not Started | Pixel installed, audience accumulating | Start building the audience NOW. You need 300+ in the pool before retargeting works.
22 | Phase 0: Pre-Launch | Hiring | Hire/contract marketing ops person | Find a part-time marketing ops contractor ($2-3K/month): manage ad campaigns, schedule social posts, set up email sequences, handle initial support tickets. Source from Upwork, LinkedIn, or your network. Must start by March 10. | Rishi | P0 - Critical | None | 2026-02-17 | 2026-03-07 | 19 | Not Started | Contractor onboarded and managing ad + email ops | You CANNOT be CEO, PM, marketer, salesperson, and support agent simultaneously during launch. This is the #1 operational risk.
WEEKS 3-4: Mar 1-14 — Build & Test
23 | Phase 0: Pre-Launch | Marketing | LinkedIn posts: Weeks 5-6 of content plan | Posts 13-18: Instant Answer Workflow, Speed Benchmarks, Execution Plan Template, Retiring Month-End, Automated Accruals Guide, Scaling Without Headcount. | Rishi | P1 - High | None | 2026-03-02 | 2026-03-14 | 13 | Not Started | 6 posts published, engagement rate tracked | Keep the cadence. Do not skip.
24 | Phase 0: Pre-Launch | Marketing | Prepare Product Hunt listing | Write tagline, description, 5 screenshots, maker story. Line up a hunter (ideally a known PH community member). Plan first-hour voting: notify your network 24h in advance. Target launch date: April 8-10 (Week 2, not April 1). | Rishi | P2 - Medium | None | 2026-03-03 | 2026-03-14 | 12 | Not Started | Full PH listing draft ready, hunter confirmed | PH in Week 2, not Week 1. Let Week 1 users validate the product first.
25 | Phase 0: Pre-Launch | Marketing | Draft 3-email launch sequence | Email 1 (Apr 1): Launch announcement — what Larry is, what it does, direct link to signup. Email 2 (Apr 3): Feature deep-dive — show Larry in action with real examples. Email 3 (Apr 7): Social proof — early user reactions + CTA. | Rishi | P1 - High | None | 2026-03-03 | 2026-03-10 | 8 | Not Started | 3 emails drafted, tested, loaded into email platform | Simple, direct, CTA-focused. No fluff.
26 | Phase 0: Pre-Launch | Sales | Begin partner outreach to accounting firms | Identify 5-10 accounting firms serving Series A-C companies. Pitch: 'We give your clients free Larry access. When they need close automation, you get implementation fees.' Schedule intro calls for April. | Rishi | P2 - Medium | None | 2026-03-03 | 2026-03-14 | 12 | Not Started | 5 firms contacted, 2-3 intro calls scheduled | This is the partner-channel revenue stream ($150K-$250K target).
27 | Phase 0: Pre-Launch | Marketing | Prepare launch day social media plan | Launch day (Apr 1): LinkedIn post (Post 27), Twitter/X post, email blast. Day 2-7: Daily posts with early user reactions, Larry screenshots, engagement prompts. Pre-write all content. | Rishi | P1 - High | None | 2026-03-10 | 2026-03-21 | 12 | Not Started | 7 days of launch content pre-written and scheduled | Do not wing launch week. Pre-write everything.
WEEKS 5-6: Mar 15-31 — Final Prep & Soft Launch
28 | Phase 0: Pre-Launch | Marketing | Execute 'Roast My Ledger' campaign (Post 19) | LinkedIn post: 'Send me your sanitized ledger. I'll run Larry's audit and send you 3 insights you missed.' Commit to 10-20 audits. Each = warm lead + potential case study. Must deliver insights within 24 hours. | Rishi | P1 - High | Larry QA against 50 datasets complete | 2026-03-17 | 2026-03-28 | 12 | Not Started | 10+ ledger audits completed and shared back | Your best lead-gen idea. Make it real. 24-hour turnaround is critical.
29 | Phase 0: Pre-Launch | Marketing | LinkedIn Phase 3 content: Weeks 7-8 | Posts 19-24: Roast My Ledger, Feature Comparison Matrix, Why We Built It Manifesto, Early Access Fast Track, First Query Prompt, Pricing ROI Calculator. Larry is NOW revealed by name. | Rishi | P1 - High | None | 2026-03-17 | 2026-03-28 | 12 | Not Started | 6 posts published; waitlist/early access signups tracked | The reveal phase. Larry goes from mechanism to named product.
30 | Phase 0: Pre-Launch | Marketing | Send early access to confirmed influencers | Give 5+ influencers access to Larry on their own books. Ask them to try it live and share their honest reaction. Provide a simple brief: 'Connect your ERP, ask Larry these 3 questions, tell us what you think.' | Rishi | P1 - High | Influencer outreach completed + product QA passed | 2026-03-21 | 2026-03-28 | 8 | Not Started | 3+ influencers post or commit to posting about Larry | Authentic > scripted. Let them find value organically.
31 | Phase 0: Pre-Launch | Operations | Brief launch week support team | Assign roles for April 1-7: (1) Product/bug monitor — Anirudh, (2) Support ticket response <1 hour — marketing ops contractor, (3) Community + social monitoring — Rishi, (4) Backup escalation path. Create shared Slack channel. | Rishi | P1 - High | Marketing ops hire complete | 2026-03-28 | 2026-03-31 | 4 | Not Started | All roles assigned with documented escalation path | If someone tweets 'my ERP connection failed' and no one responds for 6 hours, that's reputational damage.
32 | Phase 0: Pre-Launch | Marketing | LinkedIn launch week content: Week 9 | Posts 25-27: Final Checks (Mar 30), Manifesto Redux (Mar 31), MEET LARRY Launch Post (Apr 1). Post 27 must be: problem → solution → CTA (link to signup). No philosophy. Direct path from post to product. | Rishi | P0 - Critical | None | 2026-03-28 | 2026-04-01 | 5 | Not Started | Launch post gets 50+ comments and 100+ reactions | Do NOT bury the CTA. Clear path from post to product.
33 | Phase 0: Pre-Launch | Product | Prepare support/FAQ documentation | Create help docs for: ERP connection (per ERP), common Larry queries, Close Tracker basics, upgrade flow, billing FAQ. Host on help center or knowledge base. | Anirudh | P1 - High | Product QA complete | 2026-03-21 | 2026-03-28 | 8 | Not Started | Help docs cover top 20 anticipated questions | Users who can self-serve support don't become tickets.
WEEK 7: Apr 1-7 — LAUNCH WEEK (Controlled)
34 | Phase 1: Launch Month | Marketing | April 1: Launch post + email blast + social | Execute launch: LinkedIn Post 27 live by 9 AM. Email blast to full list. Twitter/X post. Personal DMs to 20 key people in your network. All pre-written content goes live per schedule. | Rishi | P0 - Critical | All Phase 0 complete | 2026-04-01 | 2026-04-01 | 1 | Not Started | Day 1 signups: 50+ | This is the moment. Execute the plan. Do not improvise.
35 | Phase 1: Launch Month | Marketing | Activate Google AdWords (branded terms only) | Turn on branded campaigns only: 'Komplai,' 'Larry AI finance.' Budget: Rs. 10,000/week ($120). Monitor CPC, CTR, conversion to signup. Do NOT activate competitor or category terms yet. | Rishi | P1 - High | Launch day | 2026-04-01 | 2026-04-07 | 7 | Not Started | Branded ads live with <$3 CPC and >2% CTR | Start with branded. Scale to long-tail in Week 2 if branded performs.
36 | Phase 1: Launch Month | Product | Daily monitoring dashboard: Week 1 | Every morning at 9 AM, review: signups (total + daily), ERP connections (total + rate), first Larry queries (total + rate), return visits (Day 1 retention). Share dashboard with Rishi. Flag if ERP connection rate <40% or first-query rate <60%. | Anirudh | P0 - Critical | Funnel tracking live | 2026-04-01 | 2026-04-07 | 7 | Not Started | Dashboard reviewed daily; issues flagged within 4 hours | If connection rate <40%, there is a UX problem. Fix before scaling traffic.
37 | Phase 1: Launch Month | Sales | Personal outreach to every Week 1 user | Message every single user who signs up in Week 1. Ask: What brought you here? What did you try first? What worked? What didn't? Use LinkedIn DM, email, or in-product chat. Log responses in spreadsheet. | Rishi | P0 - Critical | Launch day | 2026-04-01 | 2026-04-07 | 7 | Not Started | 30+ user conversations logged with qualitative feedback | This qualitative data is worth more than any analytics dashboard.
38 | Phase 1: Launch Month | Product | Fix onboarding friction identified in Week 1 | From daily monitoring + user feedback, identify and fix the top 3 friction points. Target <24-hour fix cycle for critical issues. Prioritize: ERP connection failures > Larry accuracy issues > UX confusion. | Anirudh | P0 - Critical | Daily monitoring active | 2026-04-02 | 2026-04-07 | 6 | Not Started | Top 3 friction points identified and fixed | Speed of response in Week 1 determines whether the launch has legs.
WEEK 8: Apr 8-14 — Iterate & Scale
39 | Phase 1: Launch Month | Marketing | Product Hunt launch | Launch on PH (target Tuesday or Wednesday). Execute voting plan: notify network 24h before. Rishi: respond to every PH comment within 1 hour. Target: 500+ upvotes, Top 5 of the day. | Rishi | P1 - High | Week 1 product issues fixed | 2026-04-08 | 2026-04-10 | 3 | Not Started | 500+ upvotes, 200+ signups from PH | PH can deliver 500-2000 signups in a single day if prepared properly.
40 | Phase 1: Launch Month | Marketing | Scale Google AdWords: add long-tail keywords | Add long-tail campaigns: 'MIS automation,' 'AI finance assistant for CFOs,' 'why does month end close take so long.' Add competitor terms: 'Numeric alternatives.' Budget: Rs. 15,000/week ($180). Create dedicated landing pages per keyword group. | Rishi | P1 - High | Branded ads performing | 2026-04-08 | 2026-04-14 | 7 | Not Started | Long-tail campaigns live with <$10 CPC | Only scale what converts to activated users, not just signups.
41 | Phase 1: Launch Month | Marketing | Shift LinkedIn content: 'What Larry found' posts | Move from educational content to demonstration content. Share anonymized Larry insights from real user data (with permission). Show actual charts, analysis, and answers Larry produced. 3x/week continues. | Rishi | P1 - High | Launch complete | 2026-04-08 | 2026-04-30 | 23 | Not Started | 3 posts/week showing real Larry outputs | Show, don't tell. Demonstrated value > theoretical value.
42 | Phase 1: Launch Month | Marketing | Fix existing SEO articles (batch 2: articles 21-50) | After batch 1 (top 20) title rewrites, continue with articles 21-50. Same formula: benefit + timeframe titles, proof + emotion meta descriptions, add schema markup. | Rishi | P2 - Medium | Batch 1 done (Feb) | 2026-04-08 | 2026-04-21 | 14 | Not Started | 50 total articles optimized; CTR improvement tracked | SEO compounds. These fixes pay off in May-June.
43 | Phase 1: Launch Month | Sales | First sales outreach from Larry trigger signals | Users who triggered sales handoff notifications get personalized outreach. Reference their actual Larry usage. Goal: start 5+ enterprise conversations in Week 2-3. | Rishi | P1 - High | Sales triggers operational | 2026-04-08 | 2026-04-21 | 14 | Not Started | 5+ enterprise conversations initiated | These warm leads are 10x more valuable than cold outbound.
WEEKS 9-10: Apr 15-30 — First Conversions
44 | Phase 1: Launch Month | Marketing | Trigger upgrade email sequence | For users who signed up Weeks 1-2 and used Larry 5+ times: Day 1 email: 'You've asked Larry [X] questions. Scaling gives you unlimited.' Day 3: 'Your team could save [Y] hours.' Day 7: Direct upgrade offer with annual discount. | Rishi | P0 - Critical | Upgrade flow built + enough users | 2026-04-15 | 2026-04-22 | 8 | Not Started | Email sequence triggers for all eligible users; 5%+ open-to-upgrade rate | This is where self-serve revenue starts.
45 | Phase 1: Launch Month | Product | Surface month-end Close Tracker insights proactively | As April month-end approaches (Apr 25-30), push Close Tracker notifications: 'Your April close is X% complete. At current pace, estimated close: Day Y.' Free tier shows basic progress. Scaling shows predictions + bottlenecks. | Anirudh | P1 - High | Close Tracker built | 2026-04-22 | 2026-04-30 | 9 | Not Started | Close Tracker notifications sent to all connected users | Close Tracker is the wedge into paid. Month-end is when it shines.
46 | Phase 1: Launch Month | Marketing | Compile first case study from early adopter | Identify the most engaged user from Week 1-2 signups. Ask for a 15-min call. Document: their problem, how Larry helped, time saved, specific insights. Draft a 1-page case study with before/after metrics. | Rishi | P1 - High | Users with 2+ weeks of usage | 2026-04-21 | 2026-04-30 | 10 | Not Started | 1 case study draft with real metrics | You need social proof for May scaling.
47 | Phase 1: Launch Month | Marketing | Activate LinkedIn retargeting ads | Website visitor retargeting with CFO/Controller/Finance Director titles. Budget: Rs. 15,000/month ($180). Creative: 'Your peers are using Larry to close faster. Try it free.' Link to signup. | Rishi | P2 - Medium | LinkedIn pixel installed + 300+ in audience pool | 2026-04-15 | 2026-04-30 | 16 | Not Started | Retargeting ads live with tracked conversions | Only activate if audience pool is 300+. Otherwise, wait.
48 | Phase 1: Launch Month | Operations | Month-end review: April metrics + learnings | Full review: signups, ERP connections, activation rate, questions asked, retention (Day 1/3/7), paid conversions, MRR, enterprise pipeline. Document: what worked, what didn't, what to change for May. Share with team. | Rishi | P0 - Critical | Month end | 2026-04-28 | 2026-04-30 | 3 | Not Started | Written review with data tables + decisions for May | This review drives every May decision. Do not skip.
PHASE 2: May 1-31 — Growth & Sales Activation
49 | Phase 2: Growth Month | Product | Launch Growth tier ($499/mo) | Activate Growth tier with: JV Automation (AP/AR), AI-assisted bank recon (Fast Track), weekly validation workflows, email sync. Self-serve with optional onboarding call. | Anirudh | P0 - Critical | Phase 1 learnings | 2026-05-01 | 2026-05-07 | 7 | Not Started | Growth tier live and purchasable | This bridges the 10x gap between Scaling ($199) and Enterprise ($10K+).
50 | Phase 2: Growth Month | Product | Full Close Tracker features (Scaling+) | Enable timeline predictions and bottleneck analysis for Scaling/Growth users. 'Based on last 6 closes, you finish on Day 8. You're on pace for Day 10.' 'Bank recon is your slowest step.' | Anirudh | P1 - High | Basic Close Tracker live | 2026-05-01 | 2026-05-15 | 15 | Not Started | Timeline predictions accurate within 2 days for test accounts | Full Close Tracker is the primary upgrade driver.
51 | Phase 2: Growth Month | Marketing | Double down on converting channels | Review April data. Identify which channels produced activated users (not just signups). Reallocate May budget: increase spend on channels with >50% activation rate, cut channels with <30% activation rate. | Rishi | P0 - Critical | April month-end review | 2026-05-01 | 2026-05-05 | 5 | Not Started | May budget allocated based on April activation data | A channel that produces signups but low activation is a vanity metric. Kill it.
52 | Phase 2: Growth Month | Marketing | Google AdWords: increase to Rs. 60,000 for May | Add competitor keywords performing from April tests. Create dedicated landing pages for top 3 performing keyword groups. Budget: Rs. 60,000/month ($720). | Rishi | P1 - High | April ad performance data | 2026-05-05 | 2026-05-31 | 27 | Not Started | CPA (cost per activated user) tracked and <$50 | Only scale what converts to activated users.
53 | Phase 2: Growth Month | Sales | Warm outbound from Larry usage data | Users who hit question limits, explore multi-entity, or show consistent Close Tracker bottlenecks → personalized outreach referencing their actual usage. Target: 5-8 enterprise conversations in May. | Rishi | P0 - Critical | Sales triggers operational | 2026-05-05 | 2026-05-31 | 27 | Not Started | 5-8 enterprise conversations; $200K-$400K pipeline | This is where the real revenue lives. Prioritize over self-serve optimizations.
54 | Phase 2: Growth Month | Sales | Direct outbound to ICP (10 target accounts) | Identify 10 Series A-C companies with 10+ finance teams. Use 'Roast My Ledger' as hook: 'We'll run a free AI audit of your close process.' Personalized emails to CFO/Controller. | Rishi | P1 - High | None | 2026-05-05 | 2026-05-31 | 27 | Not Started | 10 outbound emails sent; 3+ responses | Supplement Larry-sourced leads with targeted outbound.
55 | Phase 2: Growth Month | Partnerships | Execute accounting firm partner meetings | Meet with 3-5 firms from March outreach. Present partnership model: free Larry for their clients, implementation fees for close automation. Sign 1-2 partners by May 31. | Rishi | P1 - High | March partner outreach | 2026-05-05 | 2026-05-31 | 27 | Not Started | 1-2 accounting firm partners signed | Partner channel = $150K-$250K target. Needs to start producing in June.
56 | Phase 2: Growth Month | Marketing | Community engagement: Reddit, Slack, forums | Weekly participation in r/accounting, r/CFO, finance Slack groups. Answer questions. Share frameworks. Mention Komplai only when relevant. 3-5 substantive contributions per week. | Rishi | P2 - Medium | None | 2026-05-01 | 2026-05-31 | 31 | Not Started | 15+ community contributions; tracked referral traffic | Slow burn, high quality. Best leads come from genuine participation.
57 | Phase 2: Growth Month | Marketing | Launch referral program for existing users | Offer existing users 3 months of Scaling free for every referral that converts to paid. Simple referral link/code. Track: referrals sent, signups from referrals, conversions. | Rishi | P2 - Medium | Paying users exist | 2026-05-15 | 2026-05-31 | 17 | Not Started | Referral program live; 10+ referrals generated | Costs nothing but deferred revenue. Your best users are your best salespeople.
58 | Phase 2: Growth Month | Marketing | Publish first case study | Finalize April case study. Publish on website, share on LinkedIn, include in sales outreach. Format: problem → Larry solution → results (with numbers). | Rishi | P1 - High | Case study draft from April | 2026-05-05 | 2026-05-12 | 8 | Not Started | Case study published; used in 5+ sales conversations | Social proof accelerates everything.
59 | Phase 2: Growth Month | Operations | Month-end review: May metrics + learnings | Full review: cumulative signups, paid conversions (Scaling + Growth), MRR, enterprise pipeline, partner progress. Compare to targets. Adjust June plan. | Rishi | P0 - Critical | Month end | 2026-05-28 | 2026-05-31 | 4 | Not Started | Written review with revised June targets | By now you should know if the model works.
PHASE 3: Jun-Sep — Acceleration & Enterprise Revenue
60 | Phase 3: Acceleration | Sales | Close first 2-3 Enterprise deals | Convert April-May pipeline. Target: 2-3 deals at $20K-$30K each. Use case studies, live demos on their data, Larry usage history as proof points. | Rishi | P0 - Critical | May pipeline built | 2026-06-01 | 2026-06-30 | 30 | Not Started | $40K-$90K from enterprise in June | Enterprise is where the revenue math works.
61 | Phase 3: Acceleration | Product | Enterprise tier positioning: full Book Close | Position full Book Close module for Enterprise pipeline. Multi-entity consolidation, maker-checker workflows, custom integrations. Prepare demo flow for Enterprise sales calls. | Anirudh | P1 - High | Growth tier stable | 2026-06-01 | 2026-06-30 | 30 | Not Started | Enterprise demo flow documented and tested | Enterprise deals need a polished story.
62 | Phase 3: Acceleration | Marketing | Scale content + SEO to drive organic traffic | Publish 4-6 new high-intent articles per month using optimized formula. Topics from keyword research: 'close automation for startups,' 'AI reconciliation software,' 'MIS report automation.' SEO should be producing 2,000+ organic visits/month by August. | Rishi | P1 - High | SEO fixes from Feb-May | 2026-06-01 | 2026-09-30 | 122 | Not Started | Organic traffic growing 20%+ month-over-month | Content compounds. June articles pay off in August-September.
63 | Phase 3: Acceleration | Sales | Scaling → Growth upsells | Identify Scaling users who would benefit from Growth features (JV automation, bank recon). Target 10-15% upgrade rate. In-product prompts during close periods: 'Automate this bottleneck with Growth plan.' | Rishi | P1 - High | Growth tier live + users on Scaling | 2026-06-15 | 2026-09-30 | 108 | Not Started | 10-15% of Scaling users upgrade to Growth | Expansion revenue is the cheapest revenue.
64 | Phase 3: Acceleration | Partnerships | Partner channel producing referrals | Signed accounting firm partners should be referring clients. Target: 2-3 referral deals per month at $10K-$20K. Provide partners with Larry demo access and sales collateral. | Rishi | P1 - High | Partners signed in May | 2026-06-15 | 2026-09-30 | 108 | Not Started | 2-3 partner referral deals/month by August | Partner revenue = $150K-$250K over 6 months. Needs consistent nurturing.
65 | Phase 3: Acceleration | Operations | Monthly revenue reviews (Jun, Jul, Aug, Sep) | Monthly review of: self-serve MRR, enterprise deals closed, partner revenue, total cumulative. Compare to 3-stream model targets. Adjust channels every 2 weeks. | Rishi | P0 - Critical | Monthly cadence | 2026-06-30 | 2026-09-30 | 93 | Not Started | Monthly reviews with documented decisions | Kill what doesn't work. Double down on what does.

## Dashboard
LAUNCH PLAN DASHBOARD
TASK SUMMARY
Category | Rishi | Anirudh | Total | P0 Tasks | Key Deadline
Product/Engineering | 0 | 14 | 14 | 8 | Mar 28: Final QA
Marketing | 16 | 0 | 16 | 3 | Apr 1: Launch day
Sales | 5 | 0 | 5 | 2 | May 31: Pipeline $200K+
Partnerships | 2 | 0 | 2 | 0 | May 31: 1-2 partners signed
Operations/Hiring | 4 | 0 | 4 | 3 | Mar 7: Marketing ops hired
TOTAL | 27 | 14 | 41 | 16
REVENUE TARGETS (6-MONTH)
Stream | Target | Mechanism | Confidence | Key Milestones
Self-serve (Scaling + Growth) | $150K-$250K | PLG funnel | Medium | 200-400 paying subs by Sep
Sales-assisted Enterprise | $400K-$600K | Larry signals + outbound | Med-High | 10-15 deals at $20K-$40K
Partner / Channel | $150K-$250K | Accounting firm referrals | Low-Med | 2-3 deals/month by Aug
TOTAL | $700K-$1.1M |  |  | Realistic: $420K-$680K
MONTHLY SUCCESS METRICS
Month | Signups | Paid Users | MRR | Enterprise Pipeline
April | 200-400 | 10-25 | $2K-$7K | $50K-$100K
May | 600-1,000 | 40-90 | $8K-$18K | $200K-$400K
June | 1,000-1,600 | 80-150 | $15K-$30K | $300K-$500K
July | 1,400-2,200 | 120-220 | $22K-$42K | $400K-$600K
August | 1,800-2,800 | 160-300 | $30K-$55K | $500K-$700K
September | 2,200-3,500 | 200-400 | $40K-$70K | $600K-$800K

## Budget
MARKETING BUDGET ALLOCATION (Rs. 6,00,000 / ~$7,200)
Channel | Allocation % | Total (Rs.) | Apr | May | Jun-Sep | Notes
SEO + Content Optimization | 35% | 210000 | 30000 | 40000 | 140000 | Fix CTR first, then new content
Google AdWords (branded + long-tail) | 25% | 150000 | 40000 | 60000 | 50000 | Only long-tail + branded. No expensive category bids.
Launch Event + Product Hunt | 15% | 90000 | 60000 | 15000 | 15000 | Front-loaded for April launch
LinkedIn Retargeting | 15% | 90000 | 15000 | 25000 | 50000 | CFO/Controller titles only. Activate after 300+ pool.
Community + Partnerships | 10% | 60000 | 10000 | 20000 | 30000 | Event sponsorships, firm outreach, tools
TOTAL | 100% | 600000 | 155000 | 160000 | 285000